F5 BIG-IP SSL Policy Enhancement Project Plan

Project Name: F5 BIG-IP SSL Policy Enhancement
Version: 1.0
Date: 2026-01-21
Project Owner: Bronson So

1 Background

The company needs to enhance SSL/TLS security policies on F5 BIG-IP devices, implementing differentiated encryption standards based on traffic origin:

External Traffic: Enforce TLS 1.2 and above, disable TLS 1.0 and 1.1

Internal/Trusted Domain Traffic: Allow TLS 1.0, 1.1, 1.2, and 1.3

2 Objectives

Enforce HTTPS TLS 1.2+ with modern cipher suites for external traffic

Standardize all SSL profiles based on 3 security templates (Legacy, Standard, High)

Implement intelligent SSL selection based on source IP using existing Data Groups

3 Scope

Included:

F5 BIG-IP SSL Profile configuration and cipher standardization

Tls 1.0, 1.1 external traffic capture on F5 BIG-IP or mirror port on switch

iRule development for dynamic SSL selection

TLS versions and cipher suite standardization across prod and uat environments

Excluded:

Application-level TLS configuration modifications

SSL policy adjustments on non-F5 devices

Hardware SSL offloading performance tuning

Client-side application updates

2. Current Environment Analysis

2.1 F5 Device Information

| Item | Information |
| --- | --- |
| Device Names | F5 BIG-IP |
| Software Version | 17.5.1.3 Build 0.192.19 Engineering Hotfix |
| Deployment Environment | Production (prod) and UAT (uat) environments |
| Partitions | common, prod, uat |

2.2 Current SSL/TLS Configuration

2.2.1 Overview

32 client SSL profiles with clear separation between Production (prod) and UAT (uat) environments (appendix I)

Hierarchical design using template profiles for consistent security policies (appendix II)

Two primary certificate chains: hkec.chain.crt (prod) and u_hkec.chain.crt (uat)

2.2.2 SSL Profile Configuration

| Name | Security Level | No. of Profile | TLS Version | Cipher Posture |
| --- | --- | --- | --- | --- |
| High | High | 11 | 1.2 + | Cipher posture: GCM-only (AES-GCM) and/or CHACHA20 only Forward secrecy: PFS-capable suites only (ECDHE/DHE) No CBC suites detected No SHA1 / RC4 / 3DES / NULL / EXPORT / MD5 indicators detected |
| Standard | Medium | 7 | 1.2 + | Cipher posture: includes CBC-mode suites (typically SHA256) May still include GCM suites, but not strictly GCM-only No SHA1 / weak suite indicators detected |
| Legacy | Low | 14 | 1.0 + | Cipher posture: allows deprecated SHA1 suites and/or non‑PFS RSA key exchange suites (compatibility) Often includes CBC suites and legacy-compatible RSA suites Highest compatibility, lowest security posture among the four classes |

2.2.3 SSL Profile Usage Pattern (TBC)

| Services | Network | SSL Profile |
| --- | --- | --- |
| AI Services | External | High |
|  | Internal | Low |
| EDB Applications | External | High |
|  | Internal | Low |
| Project Sites | External | Standard |
|  | Internal | Low |
| General Services | External | Standard |
|  | Internal | Low |
| Management | External | High |
|  | Internal | Low |

2.3 Identified Network and IP Ranges

Internal Network:

Class A network

From 10.0.0.0 to 10.5.x.x

using 22,23,24,26 subnets

External Network:

202.8.88.0/22

210.5.185.66/32

220.241.141.1/32

20.187.162.128/32

20.187.187.28/32

2.4 Other Services

The following services are not included in this project

| Services |  |
| --- | --- |
| SMTP | ltm data-group internal prod/mbox_smtp_nosnat { 10.0.0.116/32 { } 10.0.0.123/32 { }} |
| LDAPS | ltm monitor ldap prod/hkec_ldap { destination *:* # Could be port 389 (LDAP) or 636 (LDAPS)} |
| MySQL | ltm monitor mysql prod/proxysql_6033 { destination *:6033} |
| FTPS | ltm monitor tcp uat/u_hkec_ftps { destination *.ftp} |

3. Technical Implementation Plan

3.1 Implementation

Description: Enable logging on F5 BIG-IP devices to capture TLS 1.0/1.1 external traffic. Log will be recorded on the load balancer or syslog server (if exist) and exported for analysis after 1 week. Management will then decide how to proceed with the unification of SSL profiles on F5

Approach: Gradual rollout from a few selected IPs to full IP coverage in both UAT and Production.

3.2.1 Phase 1: Discovery & Assessment

| Item | Activity | Description | Key Deliverables | Timeline |
| --- | --- | --- | --- | --- |
| 1. | Enable TLS traffic logging | Configure F5 security logging to capture TLS version details for all external connections. | - iRule to log Client Hello TLS version - Logging profile configured - Initial traffic sample captured | Week 1 |
| 2. | Establish reporting baseline | Report on: source IPs, time, frequency, applications accessed, user agents (if possible). | - Daily/Weekly TLS version report - Top offending source IPs list | Week 1 |
| 3. | Identify business-critical exemptions | Engage application owners to identify any legacy systems that may require TLS 1.0/1.1. | - List of applications/devices requiring exemption | Week 2 |

3.2.2 Phase 2: Preparation & Gradual Enforcement

| Item | Activity | Description | Key Deliverables | Timeline |
| --- | --- | --- | --- | --- |
| 4. | Create blocking iRule/policy | Develop a blocking iRule that: 1. Logs and alerts on TLS 1.0/1.1 external traffic but does not block (dry-run). | - iRule for logging/blocking - Test plan | Week 3 |
| 5. | Test in non-production | Apply iRule/policy in pre-production environment and validate with legacy clients. | - Validation report - Updated exemption list | Week 4 |
| 6. | Schedule change window | Coordinate with stakeholders for production deployment during a low-risk maintenance window. | - Approved change request - Rollback plan documented | Week 4 |

3.2.3 Phase 3: Implementation

| Item | Activity | Description | Key Deliverables | Timeline |
| --- | --- | --- | --- | --- |
| 7. | Deploy in "detect-only" mode | Apply iRule/policy in production with logging but no blocking. Verify logs match expectations. | - Production logs verified - Alerting configured for any unexpected traffic | Week 5 |
| 8, | Enable blocking | After confirmatory period (e.g., 7 days), enable blocking. Monitor for incidents. | - Blocking enabled - Incident response team briefed | Week 6 |
| 9. | Monitor post-block traffic | Ensure all TLS 1.0/1.1 traffic is blocked except for pre-approved exemptions (handled via separate VIP/client SSL profile). | - Zero unapproved TLS 1.0/1.1 connections - Confirmation report | Week 6 |

3.2.4 Phase 4: Post-Implementation

| Item | Activity | Description | Key Deliverables | Timeline |
| --- | --- | --- | --- | --- |
| 10. | Document & review | Update documents to reflect new TLS baseline. | - Updated documentation - Lessons learned report | Week 7 |

5. Staged Deployment Strategy

The deployment will follow the recommended order:

Low-traffic production VIPs (10%)

Medium-traffic VIPs (40%)

High-traffic VIPs (remaining)

5.1 Rollback Plan

1. Immediate Rollback (0-15 minutes)

- Remove iRule from VIP

- Reapply original SSL profile

- Verify service restoration

2. Extended Rollback (15-60 minutes)

- Restore from configuration backup

- Reload configuration

- Full service validation